## LEAD SLA
LEAD Content Upload Road Map
Item | Section | Sub Section | Content / Month | Content / Channel | Responsible | Content Upload
Be in the LEAD | Trending Now |  | 8 | Videos, Articles etc. | Naely 4 - Nadia 4 | Every Sunday & Tuesday - 2 contents
| Top Management Interviews |  | 2 | Videos | Naely | 1st & 3rd Sunday
| Leadership podcast |  | 2 | Podcast | Naely | 1st & 3rd Tuesday
| Learning archive |  | To be moved | Last Month Contents | Fatma | On 25th of every Month
| LinkedIn learning |  | 8 | iGrow | Naely/Nadia | Every Wednesday 2 courses
| Leadership Tips |  | 4 | Videos | Ayman, Naely, Nadia, Fatma | Every Sunday
| Live Sessions | Lead Live Sessions (PM) | 2 | Microsoft Teams | Fatma | Every 25th
|  | MINT ( 4 sessions per trainer) | 8 | Microsoft Teams | Fatma | Every 25th
|  | Open Courses | 2 | Microsoft Teams | Fatma | Every 25th
| Quote |  | 20 | Rotating Banner & Picture | All | 5 pictures every Sunday (Starting November)
| Book |  | 2 | Rotating Banner & pdf | Ayman | 2nd & 4th Monday
How to LEAD | Lead Yourself | Find your Strengths |  | Video | Ayman | Static. Reviewed on a monthly basis and to be added whenever required.
|  |  |  | Article | Ayman
|  | Happiness & Wellbeing |  | Video | Ayman
|  |  |  | Article | Ayman
|  | Learning Mindset |  | Video | Ayman
|  |  |  | Article | Ayman
|  | Self- Motivation |  | Video | Ayman
|  |  |  | Article | Ayman
| Lead for Performance | Hiring & Retaining Talents |  | Video | Ayman
|  |  |  | Article | Ayman
|  | Setting Goals |  | Video | Ayman
|  |  |  | Article | Ayman
|  | Great Feedback |  | Video | Ayman
|  |  |  | Article | Ayman
|  | Coach |  | Video | Ayman
|  |  |  | Article | Ayman
|  | High Performing Teams |  | Video | Ayman
|  |  |  | Article | Ayman
|  | Reviewing Performance |  | Video | Ayman
|  |  |  | Article | Ayman
|  | Managing High Performers |  | Video | Ayman
|  |  |  | Article | Ayman
|  | Culture of Engagement |  | Video | Ayman
|  |  |  | Article | Ayman
| Lead the business | Business Acumen |  | Video | Ayman
|  |  |  | Article | Ayman
|  | Operational xcellence |  | Video | Ayman
|  |  |  | Article | Ayman
|  | Leading Projects |  | Video | Ayman
|  |  |  | Article | Ayman
|  | Mastering Ms Excel |  | Video | Ayman
|  |  |  | Article | Ayman
| Lead for Growth | Leading Change |  | Video | Ayman
|  |  |  | Article | Ayman
|  | Digital Transformation |  | Video | Ayman
|  |  |  | Article | Ayman
|  | Growth Strategies |  | Video | Ayman
|  |  |  | Article | Ayman
LEAD with Competencies | Managing Complexity | LinkedIn Learning Collections | Static | iGrow | Nadia | To be reviewed on a montly basis and added whenever required.
|  | Action Plan | Static | Picture | Nadia | Static
|  | Article |  | PDF | Nadia | To be added in November 2020
| Working Across Boundaries | LinkedIn Learning Collections | Static | iGrow | Ayman | To be reviewed on a montly basis and added whenever required.
|  | Action Plan | Static | Picture | Ayman | Static.
|  | Article |  | PDF | Ayman | To be added in November 2020
| Delighting Our Customers | LinkedIn Learning Collections | Static | iGrow | Ayman | To be reviewed on a montly basis and added whenever required.
|  | Action Plan | Static | Picture | Ayman | Static.
|  | Article |  | PDF | Ayman | To be added in November 2020
| Influencing Others | LinkedIn Learning Collections | Static | iGrow | Nadia | To be reviewed on a montly basis and added whenever required.
|  | Action Plan | Static | Picture | Nadia | Static.
|  | Article |  | PDF | Nadia | To be added in November 2020
| Engaging Leadership | LinkedIn Learning Collections | Static | iGrow | Nadia | To be reviewed on a montly basis and added whenever required.
|  | Action Plan | Static | Picture | Nadia | Static.
|  | Article |  | PDF | Nadia | To be added in November 2020
| Developing Talent | LinkedIn Learning Collections | Static | iGrow | Nadia | To be reviewed on a montly basis and added whenever required.
|  | Action Plan | Static | Picture | Nadia | Static.
|  | Article |  | PDF | Nadia | To be added in November 2020
| Driving for Results | LinkedIn Learning Collections | Static | iGrow | Nadia | To be reviewed on a montly basis and added whenever required.
|  | Action Plan | Static | Picture | Nadia | Static.
|  | Article |  | PDF | Nadia | To be added in November 2020
| Situational Adaptability | LinkedIn Learning Collections | Static | iGrow | Nadia | To be reviewed on a montly basis and added whenever required.
|  | Action Plan | Static | Picture | Nadia | Static.
|  | Article |  | PDF | Nadia | To be added in November 2020
| Taking Initiative | LinkedIn Learning Collections | Static | iGrow | Nadia | To be reviewed on a montly basis and added whenever required.
|  | Action Plan | Static | Picture | Nadia | Static.
|  | Article |  | PDF | Nadia | To be added in November 2020
Operations | Reports | Jam Page Reports |  | Excel | Dainis
|  | LinkedIn Reports |  | Excel | Dainis
|  | Mint & Live Sessions |  | Excel | Farah & Ellen
| Driving Engagement | Monthly Newsletter (bulletin) - What happened, Top engaged leaders, What to look forward in our LEAD Page) |  | Corporate Communications | Jane | 25th - 27th of every month
|  | One Pager to be added |  | Other Jam Pages |  | 25th - 27th of every month
| Live Session & MINT | Topics to focus on the live sessions (LEAD & Open Course) |  | On Email, To be sent to Ellen for compilation | Ayman | 30th of previous month
|  | Send out Comms to Coaches/Trainers about the month's topic and the schedule(LEAD, Open Courses and MINT Live sessions) |  | Email & Excel | Farah & Ellen | 1st of every month
|  | Coaches to fill in their sessions in the calendar (leader's compass) |  | Excel | Consultants/Coaches | 1st to 15th of every month
|  | Conduct Coach interview and mock session |  | MS Teams & PPT | Ayman | before the 20th
|  | Schedule the Sessions in Forms. Update the calender design |  |  | Farah & Ellen | 15th - 19th
|  | Share the Calendar design & form links to Fatma |  |  | Ellen | 20th of every month
|  | Upload the sessions & comms in LEAD |  |  | Fatma | 25th of every month
|  | Send out calendar invites to participants |  |  | Ellen(Lead & Open Course) & Farah(MINT) | As needed
|  | Capture attendance |  | Ellen | Ellen(Lead & Open Course) & Farah(MINT) | As needed
|  | Initiate Survey |  | Ellen | Ellen(Lead & Open Course) & Farah(MINT) | As needed
| JAM Page Contents | Submission of all contents |  | TEAMS LEAD | Naely, Ayman & Nadia | 20th of every month
|  | Action Plan Excel Sheet to be updated |  | LEAD Road Map Excel | Naely, Ayman & Nadia | 20th of every month

## Action Plan- OCT
LEAD Content Upload Road Map
Item | Section | Sub Section | Content / Month | Content / Channel | Responsible | Content Upload | Status | Date to Be Uploaded
Be in the LEAD | Trending Now |  | 8 | Article | Naely | What-got-us-here-wont-get-us-there-.pdf | DONE
|  |  |  | Article | Naely | What-makes-a-CEO-exceptional.pdf | DONE
[5 empty] | Naely | Will-artificial-intelligence-make-you-a-better-leader |  | 2020-10-11
[5 empty] | Naely | Unleashing sustainable speed in a post-COVID world_ Reimagine structure |  | 2020-10-13
[5 empty] | Naely | The-CEO-moment-Leadership-for-a-new-era-v3 |  | 2020-10-18
[5 empty] | Naely | Successfully-transitioning-to-new-leadership-roles-web-final |  | 2020-10-20
[5 empty] | Naely | Strategic decisions When can you trust your gut |  | 2020-10-25
[5 empty] | Naely | Redefining-the-role-of-the-leader-in-the-reskilling-era-vf |  | 2020-10-27
| Top Management Interviews |  | 2 | Video | Naely | Why we LEAD *EXTRA* | DONE
|  |  |  | Video | Naely | Reg_Management Interview.mp4 | DONE
|  |  |  | Video | Naely | AbdulRahman_Managament Interview.mp4 | DONE
| Leadership podcast |  | 2 | Podcast | Naely | Source_TEDx_Stop Managing, Start Leading_Hamza Khan.m4a | DONE
|  |  |  | Podcast | Naely | Source_TEDx_The surprising truth in how to be a great leader_Julia Milner.m4a | DONE
| Learning archive |  | To be moved | Last Month Contents | Fatma |  |  | 2020-10-25
| LinkedIn learning |  | 8 | iGrow | Naely | Developing Your Emotional Intelligence | DONE
|  |  |  | iGrow | Naely | Management Tips | DONE
|  |  |  | iGrow | Naely | Managing in Difficult Times | DONE
|  |  |  | iGrow | Naely | Transitioning from Manager to Leader | DONE
|  |  |  | iGrow | Naely | Human Resources: Managing Employee Problems | DONE
|  |  |  | iGrow | Naely |  |  | 2020-10-21
|  |  |  | iGrow | Naely |  |  | 2020-10-28
|  |  |  | iGrow | Naely |  |  | 2020-10-28
| Leadership Tips |  | 4 | Video | Naely | Leadership Tips_To Coach or Not to Coach | DONE
|  |  |  | Video | Naely | Leadership Tips_Importance of Listening | DONE
|  |  |  | Video | Naely | Leadership Tips_To Meet or Not to Meet | DONE
|  |  |  | Video | Naely
| Live Sessions | Lead Live Sessions (PM) | 2 | Microsoft Teams | Jessica Quelennec | Mastering Motivation for Self and Teams |  | 2020-10-06
|  |  |  | Microsoft Teams | Ahmed Ameen | Art of Delegation |  | 2020-10-15
|  |  |  | Microsoft Teams | Wael Bakhaty | Leadership Styles |  | 2020-10-27
|  | MINT ( 4 sessions per trainer) | 8 | Microsoft Teams | Ahmed Ameen | 10- Min Coaching |  | 2020-10-05
|  |  |  | Microsoft Teams | Ahmed Ameen | Powerful Feedback |  | 2020-10-05
|  |  |  | Microsoft Teams | Ahmed Ameen | Growing Your People |  | 2020-10-06
|  |  |  | Microsoft Teams | Wael Bakhaty | Setting Goals |  | 2020-10-06
|  |  |  | Microsoft Teams | Abdulla Ahmed | Conflict Resolution |  | 2020-10-07
|  |  |  | Microsoft Teams | Abdulla Ahmed | Conflict Resolution |  | 2020-10-08
|  |  |  | Microsoft Teams | Ahmed Ameen | 10- Min Coaching |  | 2020-10-12
|  |  |  | Microsoft Teams | Ahmed Ameen | Powerful Feedback |  | 2020-10-12
|  |  |  | Microsoft Teams | Ahmed Ameen | Growing Your People |  | 2020-10-13
|  |  |  | Microsoft Teams | Wael Bakhaty | Conflict Resolution |  | 2020-10-13
|  |  |  | Microsoft Teams | Abdulla Ahmed | Setting Goals |  | 2020-10-14
|  |  |  | Microsoft Teams | Abdulla Ahmed | Growing Your People |  | 2020-10-15
|  |  |  | Microsoft Teams | Ahmed Ameen | 10- Min Coaching |  | 2020-10-19
|  |  |  | Microsoft Teams | Ahmed Ameen | Powerful Feedback |  | 2020-10-19
|  |  |  | Microsoft Teams | Ahmed Ameen | Growing Your People |  | 2020-10-20
|  |  |  | Microsoft Teams | Wael Bakhaty | Setting Goals |  | 2020-10-21
|  |  |  | Microsoft Teams | Abdulla Ahmed | Conflict Resolution |  | 2020-10-22
|  |  |  | Microsoft Teams | Ahmed Ameen | 10- Min Coaching |  | 2020-10-26
|  |  |  | Microsoft Teams | Ahmed Ameen | Powerful Feedback |  | 2020-10-27
|  |  |  | Microsoft Teams | Ahmed Ameen | Growing Your People |  | 2020-10-28
|  |  |  | Microsoft Teams | Wael Bakhaty | Conflict Resolution |  | 2020-10-29
|  |  |  | Microsoft Teams | Abdulla Ahmed | Setting Goals |  | 2020-10-29
|  | Open Courses | 2 | Microsoft Teams
Microsoft Teams
| Quote |  | 5 | Picture(Rotating Banner ) | Ayman |  |  | New idea will be added in November
|  |  | 5 | Picture(Rotating Banner ) | Naely
|  |  | 5 | Picture(Rotating Banner ) | Nadia
|  |  | 5 | Picture(Rotating Banner ) | Fatma
| Book |  | 2 | PDF(Rotating Banner) | Ayman |  | DONE | 2020-10-05
|  |  |  | PDF(Rotating Banner) | Ayman |  |  | 2020-10-19
How to LEAD | Lead Yourself | Find your Strengths | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Happiness & Wellbeing | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Learning Mindset | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Self- Motivation | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
| Lead for Performance | Hiring & Retaining Talents | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Setting Goals | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Great Feedback | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Coach | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | High Performing Teams | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Reviewing Performance | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Managing High Performers | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Culture of Engagement | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
| Lead the business | Business Acumen | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Operational xcellence | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Leading Projects | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Mastering Ms Excel | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
| Lead for Growth | Leading Change | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Digital Transformation | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
|  | Growth Strategies | 1 | Video | Ayman |  | DONE
|  |  | 1 | Article | Ayman |  | DONE
LEAD with Competencies | Managing Complexity | LinkedIn Learning Collections | 4 | iGrow | Nadia |  | DONE
|  | Action Plan | 1 | Picture | Nadia |  | DONE
|  | Article | 2 | PDF | Nadia | New - To be added in NOV
| Working Across Boundaries | LinkedIn Learning Collections | 3 | iGrow | Ayman |  | DONE
|  | Action Plan | 1 | Picture | Ayman |  | DONE
|  | Article | 2 | PDF | Ayman | New - To be added in NOV
| Delighting Our Customers | LinkedIn Learning Collections | 3 | iGrow | Ayman |  | DONE
|  | Action Plan | 1 | Picture | Ayman |  | DONE
|  | Article | 2 | PDF | Ayman | New - To be added in NOV
| Influencing Others | LinkedIn Learning Collections | 3 | iGrow | Nadia |  | DONE
|  | Action Plan | 1 | Picture | Nadia |  | DONE
|  | Article | 2 | PDF | Nadia | New - To be added in NOV
| Engaging Leadership | LinkedIn Learning Collections | 3 | iGrow | Nadia |  | DONE
|  | Action Plan | 1 | Picture | Nadia |  | DONE
|  | Article | 2 | PDF | Nadia | New - To be added in NOV
| Developing Talent | LinkedIn Learning Collections | 3 | iGrow | Nadia |  | DONE
|  | Action Plan | 1 | Picture | Nadia |  | DONE
|  | Article | 2 | PDF | Nadia | New - To be added in NOV
| Driving for Results | LinkedIn Learning Collections | 3 | iGrow | Nadia |  | DONE
|  | Action Plan | 1 | Picture | Nadia |  | DONE
|  | Article | 2 | PDF | Nadia | New - To be added in NOV
| Situational Adaptability | LinkedIn Learning Collections | 5 | iGrow | Nadia |  | DONE
|  | Action Plan | 1 | Picture | Nadia |  | DONE
|  | Article | 2 | PDF | Nadia | New - To be added in NOV
| Taking Initiative | LinkedIn Learning Collections | 4 | iGrow | Nadia |  | DONE
|  | Action Plan | 1 | Picture | Nadia |  | DONE
|  | Article | 2 | PDF | Nadia | New - To be added in NOV
Operations | Reports | Jam Page Reports |  | Excel | Dainis
|  | LinkedIn Reports |  | Excel | Dainis
|  | Mint & Live Sessions |  | Excel | Farah & Ellen
| Driving Engagement | Monthly Newsletter (bulletin) - What happened, Top engaged leaders, What to look forward in our LEAD Page) |  | Corporate Communications | Jane | Draft to be approved |  | 2020-10-07
|  | One Pager to be added |  | Other Jam Pages | L&D Team | Draft to be approved |  | 2020-10-07
| Live Session & MINT | Topics to focus on the live sessions (LEAD & Open Course) |  | On Email, To be sent to Ellen for compilation | Ayman | Topics? |  | 2020-09-30
|  | Send out Comms to Coaches/Trainers about the month's topic and the schedule(LEAD, Open Courses and MINT Live sessions) |  | Email & Excel | Farah & Ellen |  |  | 2020-10-01
|  | Coaches to fill in their sessions in the calendar (leader's compass) |  | Excel | Consultants/Coaches |  |  | 1th to 15th Oct
|  | Conduct Coach interview and mock session |  | MS Teams & PPT | Ayman |  |  | Before 20th
|  | Schedule the Sessions in Forms. Update the calender design |  |  | Farah & Ellen |  |  | 15th - 19th Oct
|  | Share the Calendar design & form links to Fatma |  |  | Ellen |  |  | 2020-10-20
|  | Upload the sessions & comms in LEAD |  |  | Fatma |  |  | 2020-10-25
|  | Send out calendar invites to participants |  |  | Ellen(Lead & Open Course) & Farah(MINT) |  |  | As needed
|  | Capture attendance |  |  | Ellen(Lead & Open Course) & Farah(MINT) |  |  | As needed
|  | Initiate Survey |  |  | Ellen(Lead & Open Course) & Farah(MINT) |  |  | As needed
| JAM Page Contents | Submission of all contents |  | TEAMS LEAD Folder | Naely
|  |  |  | TEAMS LEAD Folder | Ayman
|  |  |  | TEAMS LEAD Folder | Nadia |  |  | 2020-10-20
|  | Action Plan Excel Sheet to be updated |  | LEAD Road Map Excel | Naely, Ayman & Nadia | 20th of every month |  | 2020-10-20

## Action Plan- NOV
LEAD Content Upload Road Map
Item | Section | Sub Section | Content / Month | Content / Channel | Responsible | Content Upload | Status | Date to Be Uploaded
Be in the LEAD | Trending Now |  | 8 |  | Naely | Leading-with-purpose-and-humanity-a-conversation-with-Hubert-Joly- |  | 2020-11-01
[5 empty] | Naely | Leading-agile-transformation-The-new-capabilities-leaders-need-to-build-21st-century-organizations |  | 2020-11-04
[5 empty] | Naely | Leadership-in-a-crisis-Responding-to-the-coronavirus-outbreak-and-future-challenges-v3 |  | 2020-11-08
[5 empty] | Naely | How-to-create-an-agile-organization |  | 2020-11-10
[5 empty] | Naely | How to test your decision making instincts |  | 2020-11-15
[5 empty] | Naely | From-a-room-called-fear-to-a-room-called-hope-A-leadership-agenda-for-troubled-times |  | 2020-11-17
[5 empty] | Naely | Equipping-leaders-for-merger-integration-success |  | 2020-11-22
[5 empty] | Naely | CEO-action-plan-for-workplace-automation |  | 2020-11-24
| Top Management Interviews |  | 2 | Video | Naely |  |  | 2020-11-01
|  |  |  | Video | Naely |  |  | 2020-11-15
| Leadership podcast |  | 2 | Podcast | Naely |  |  | 2020-11-03
|  |  |  | Podcast | Naely |  |  | 2020-11-17
| Learning archive |  | To be moved | Last Month Contents | Fatma |  |  | 2020-11-25
| LinkedIn learning |  | 8 | iGrow | Naely |  |  | 2020-11-04
|  |  |  | iGrow | Naely |  |  | 2020-11-04
|  |  |  | iGrow | Naely |  |  | 2020-11-11
|  |  |  | iGrow | Naely |  |  | 2020-11-11
|  |  |  | iGrow | Naely |  |  | 2020-11-18
|  |  |  | iGrow | Naely |  |  | 2020-11-18
|  |  |  | iGrow | Naely |  |  | 2020-11-25
|  |  |  | iGrow | Naely |  |  | 2020-11-25
| Leadership Tips |  | 4 | Video | Naely |  |  | 2020-11-01
|  |  |  | Video | Ayman |  |  | 2020-11-08
|  |  |  | Video | Nadia |  |  | 2020-11-15
|  |  |  | Video | Fatma |  |  | 2020-11-22
| Live Sessions | Lead Live Sessions (PM) | 2 | Microsoft Teams
Microsoft Teams
|  | MINT ( 4 sessions per trainer) | 8 | Microsoft Teams | Ahmed Ameen
|  |  |  | Microsoft Teams | Ahmed Ameen
|  |  |  | Microsoft Teams | Ahmed Ameen
|  |  |  | Microsoft Teams | Ahmed Ameen
|  |  |  | Microsoft Teams | Abdulla Ahmed
|  |  |  | Microsoft Teams | Abdulla Ahmed
|  |  |  | Microsoft Teams | Abdulla Ahmed
|  |  |  | Microsoft Teams | Abdulla Ahmed
|  |  |  | Microsoft Teams | Wael Bakhaty
|  |  |  | Microsoft Teams | Wael Bakhaty
|  |  |  | Microsoft Teams | Wael Bakhaty
|  |  |  | Microsoft Teams | Wael Bakhaty
Microsoft Teams
Microsoft Teams
Microsoft Teams
Microsoft Teams
Microsoft Teams
Microsoft Teams
Microsoft Teams
Microsoft Teams
|  | Open Courses | 2 | Microsoft Teams
Microsoft Teams
| Quote |  | 5 | Picture(Rotating Banner ) | Ayman |  |  | 2020-11-01
|  |  | 5 | Picture(Rotating Banner ) | Naely |  |  | 2020-11-08
|  |  | 5 | Picture(Rotating Banner ) | Nadia |  |  | 2020-11-15
|  |  | 5 | Picture(Rotating Banner ) | Fatma |  |  | 2020-11-22
| Book |  | 2 | PDF(Rotating Banner) | Ayman
|  |  |  | PDF(Rotating Banner) | Ayman
How to LEAD | Lead Yourself | Find your Strengths | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Happiness & Wellbeing | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Learning Mindset | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Self- Motivation | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
| Lead for Performance | Hiring & Retaining Talents | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Setting Goals | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Great Feedback | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Coach | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | High Performing Teams | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Reviewing Performance | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Managing High Performers | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Culture of Engagement | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
| Lead the business | Business Acumen | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Operational xcellence | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Leading Projects | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Mastering Ms Excel | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
| Lead for Growth | Leading Change | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Digital Transformation | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
|  | Growth Strategies | 1 | Video | Ayman
|  |  | 1 | Article | Ayman
LEAD with Competencies | Managing Complexity | LinkedIn Learning Collections |  | iGrow | Nadia
|  | Action Plan |  | Picture | Nadia
|  | Article |  | PDF | Nadia |  |  | 2020-10-25
| Working Across Boundaries | LinkedIn Learning Collections |  | iGrow | Ayman
|  | Action Plan |  | Picture | Ayman
|  | Article |  | PDF | Ayman |  |  | 2020-10-25
| Delighting Our Customers | LinkedIn Learning Collections |  | iGrow | Ayman
|  | Action Plan |  | Picture | Ayman
|  | Article |  | PDF | Ayman |  |  | 2020-10-25
| Influencing Others | LinkedIn Learning Collections |  | iGrow | Nadia
|  | Action Plan |  | Picture | Nadia
|  | Article |  | PDF | Nadia |  |  | 2020-10-25
| Engaging Leadership | LinkedIn Learning Collections |  | iGrow | Nadia
|  | Action Plan |  | Picture | Nadia
|  | Article |  | PDF | Nadia |  |  | 2020-10-25
| Developing Talent | LinkedIn Learning Collections |  | iGrow | Nadia
|  | Action Plan |  | Picture | Nadia
|  | Article |  | PDF | Nadia |  |  | 2020-10-25
| Driving for Results | LinkedIn Learning Collections |  | iGrow | Nadia
|  | Action Plan |  | Picture | Nadia
|  | Article |  | PDF | Nadia |  |  | 2020-10-25
| Situational Adaptability | LinkedIn Learning Collections |  | iGrow | Nadia
|  | Action Plan |  | Picture | Nadia
|  | Article |  | PDF | Nadia |  |  | 2020-10-25
| Taking Initiative | LinkedIn Learning Collections |  | iGrow | Nadia
|  | Action Plan |  | Picture | Nadia
|  | Article |  | PDF | Nadia |  |  | 2020-10-25
Operations | Reports | Jam Page Reports |  | Excel | Dainis
|  | LinkedIn Reports |  | Excel | Dainis
|  | Mint & Live Sessions |  | Excel | Farah & Ellen
| Driving Engagement | Monthly Newsletter (bulletin) - What happened, Top engaged leaders, What to look forward in our LEAD Page) |  | Corporate Communications | Jane | Draft to be approved |  | 2020-10-25
|  | One Pager to be added |  | Other Jam Pages | L&D Team | Draft to be approved |  | 2020-10-25
| Live Session & MINT | Topics to focus on the live sessions (LEAD & Open Course) |  | On Email, To be sent to Ellen for compilation | Ayman | Topic? |  | 2020-10-30
|  | Send out Comms to Coaches/Trainers about the month's topic and the schedule(LEAD, Open Courses and MINT Live sessions) |  | Email & Excel | Farah & Ellen |  |  | 2020-11-01
|  | Coaches to fill in their sessions in the calendar (leader's compass) |  | Excel | Consultants/Coaches |  |  | 1th to 15th Oct
|  | Conduct Coach interview and mock session |  | MS Teams & PPT | Ayman |  |  | Before 20th
|  | Schedule the Sessions in Forms. Update the calender design |  |  | Farah & Ellen |  |  | 15th - 19th Nov
|  | Share the Calendar design & form links to Fatma |  |  | Ellen |  |  | 2020-11-20
|  | Upload the sessions & comms in LEAD |  |  | Fatma |  |  | 2020-11-25
|  | Send out calendar invites to participants |  |  | Ellen(Lead & Open Course) & Farah(MINT) |  |  | As needed
|  | Capture attendance |  |  | Ellen(Lead & Open Course) & Farah(MINT) |  |  | As needed
|  | Initiate Survey |  |  | Ellen(Lead & Open Course) & Farah(MINT) |  |  | As needed
| JAM Page Contents | Submission of all contents |  | TEAMS LEAD Folder | Naely
|  |  |  | TEAMS LEAD Folder | Ayman
|  |  |  | TEAMS LEAD Folder | Nadia |  |  | 2020-11-20
|  | Action Plan Excel Sheet to be updated |  | LEAD Road Map Excel | Naely, Ayman & Nadia | 20th of every month |  | 2020-11-20